## Inc Matrix
Use Case | Use Case Name | Effort (People*Weeks) | Iteration 2* (10/25/18) | Iteration 3* (11/29/18)
UC 1 | Register | 1 X 2 | 2
UC 2 | Login | 1 X 1 | 1
UC 3 | Logout | 1 X 1 | 1
UC 4 | Update profile | 1 X 1 | 1
UC 5 | Request Rental | 1 X 2 | 2
UC 6 | View reserved rental | 1 X 1 | 1
UC 7 | Cancel reservation | 1 X 1 | 1
UC 8 | View all rentals | 1 X 1 | 1
UC 9 | View Specific Rentals | 1 X 2 | 2
UC 10 | Delete user rental |  |  | 1
UC 11 | Edit user, rental manager profile. | 1 X 1 | 1
UC 12 | Revoke renter | 1 X 2 | 2
UC 13 | Cancel revoke renter | 1 X 1 | 1
UC 14 | View available cars | 1 X 2 | 2
UC 15 | Change user role | 1 X 1 | 1
UC 16 | View Calender of cars |  |  | 1
| Total Effort Estimated |  | 19 | 2
| Total Effort Available |  | 19.5 | 24
| Team Size | 6
Sum of the efforts of each row must not be less than the required effort | * Sum of the effort of each column must not exceed the ability of the team. Sum of the efforts of each row must not be less than the required effort.
Note on C21: Robb: Enter team size here